## Slide 1: ZnNi Line Report
Generated on 2025-10-21 14:01:32
Projects: 3

## Slide 2: Project: ZnNi Line Phase 1 - Equipment Installation
Code: ZnNi-P1
Status: IN_PROGRESS
Progress: 52%
Target: 2025-12-31

## Slide 3: ZnNi Line Phase 1 - Equipment Installation - Milestones
Total Milestones: 7
Completed: 3
  • Equipment Procurement (2025-03-31)
  • Foundation Work (2025-06-30)
  • Site Preparation (2025-09-15)
In Progress: 2
  • Equipment Installation - Phase 1 (Due: 2025-10-15)
  • Equipment Installation - Phase 2 (Due: 2025-10-31)
Not Started: 2

## Slide 4: ZnNi Line Phase 1 - Equipment Installation - Risks
Total Risks: 3
HIGH Severity: 1
  • Delayed equipment delivery from overseas supplier
MEDIUM Severity: 1
  • Resource availability during holiday season
LOW Severity: 1

## Slide 5: ZnNi Line Phase 1 - Equipment Installation - Change Management
Total Changes: 2
• CHG001: Additional safety inspections required by regulatory body
  Impact: 15 day delay
• CHG002: Early completion due to favorable weather and efficient crew
  Impact: 5 day acceleration

## Slide 6: Project: Quality Management System Implementation
Code: QMS-2025
Status: IN_PROGRESS
Progress: 68%
Target: 2026-02-28

## Slide 7: Quality Management System Implementation - Milestones
Total Milestones: 8
Completed: 3
  • Requirements Gathering (2025-05-31)
  • System Design (2025-07-15)
  • Process Documentation (2025-09-30)
In Progress: 1
  • Staff Training - Wave 1 (Due: 2025-10-25)
Not Started: 4

## Slide 8: Quality Management System Implementation - Risks
Total Risks: 3
HIGH Severity: 1
  • Integration issues with legacy systems
MEDIUM Severity: 1
  • Staff resistance to new procedures
LOW Severity: 1

## Slide 9: Quality Management System Implementation - Change Management
Total Changes: 1
• CHG001: Additional training modules added based on feedback
  Impact: 10 day delay

## Slide 10: Project: IT Infrastructure Upgrade
Code: IT-INFRA-2025
Status: IN_PROGRESS
Progress: 42%
Target: 2026-03-31

## Slide 11: IT Infrastructure Upgrade - Milestones
Total Milestones: 8
Completed: 3
  • Infrastructure Assessment (2025-07-15)
  • Hardware Procurement (2025-08-31)
  • Network Backbone Upgrade (2025-09-30)
In Progress: 1
  • Server Migration - Phase 1 (Due: 2025-10-20)
Not Started: 4

## Slide 12: IT Infrastructure Upgrade - Risks
Total Risks: 4
HIGH Severity: 1
  • Extended downtime during migration
MEDIUM Severity: 2
  • Data compatibility issues post-migration
  • Budget overrun due to unforeseen technical challenges
LOW Severity: 1

## Slide 13: IT Infrastructure Upgrade - Change Management
Total Changes: 2
• CHG001: Additional security patches required before migration
  Impact: 5 day delay
• CHG002: Accelerated due to early hardware delivery and resource availability
  Impact: 20 day acceleration

## Slide 14: Overall Summary
Total Projects: 3
Total Milestones: 23
Total Risks: 10
Total Changes: 5