## Risks
ID | Project | Title | Description | Likelihood | Impact | Mitigations | Owner | Date Identified | Status | Category
R001 | SF Documentation Optimization | NADCAP Audit Preparation Delays | The SF team is very busy with many other tasks from wider stakeholders. There may be delays in completing the NADCAP action plan and SF documentation review, meaning we may not be ready for the NADCAP Audit and the pre-audit planned for March 26, 2026. | High | High | Prioritize NADCAP tasks; Allocate dedicated resource time; Weekly progress reviews; Escalate to management if delays occur | SF Team Lead | 2025-11-07 | Open | Schedule
R002 | SF Documentation Optimization | SF QMS Documentation Hierarchy Inaccuracies | If we do not fully understand the documentation hierarchy, the overarching document (the SF QMS) could have inaccuracies which defeats the objective of being able to signpost anyone unfamiliar with the documentation in SF. | Medium | High | Conduct thorough documentation hierarchy workshop; Create visual mapping of document structure; Peer review of QMS by multiple stakeholders; Include SF veterans in review process | Documentation Specialist | 2025-11-07 | Open | Quality
R003 | Surface Finish Table 1 Implementation Complete | Surface Finish Table Validation Delay | The process engineer carrying out the work for validating Surface Finish Table 1 is really busy and may not complete the review in the given timeframe. | High | Medium | Identify backup resource; Break down validation into smaller milestones; Request management support to free up engineer time; Consider parallel validation approach | Process Engineering Manager | 2025-11-07 | Open | Resource