## Risks
ID | Project | Title | Description | Likelihood | Impact | Mitigations | Owner | Date Identified | Status | Category
R001 | SF Documentation Optimization | NADCAP Audit Preparation Delay Risk | The SF team being so busy with many other tasks from wider stakeholders, there may be delays in completing the NADCAP action plan and SF documentation review, meaning we may not be ready for the NADCAP Audit and the pre-audit planned for March 26, 2025. | High | High | Prioritize NADCAP tasks; assign dedicated resources; weekly progress reviews; escalate to management if delays occur | SF Team Lead | 2025-11-07 | Open | Schedule
R002 | SF Documentation Optimization | SF QMS Documentation Hierarchy Accuracy | If we do not fully understand the documentation hierarchy, the overarching document (SF QMS) could have inaccuracies which defeats the objective of being able to signpost anyone unfamiliar with the documentation in SF. | Medium | High | Conduct documentation hierarchy workshop; peer review of QMS structure; validate with SF stakeholders; create visual documentation map | Documentation Lead | 2025-11-07 | Open | Quality
R003 | Surface Finish Table 1 Implementation Complete | Process Engineer Capacity Constraint | The process engineer carrying out the work for validating the Surface Finish Table 1 is really busy and may not complete the review in the given timeframe. | High | Medium | Identify backup engineer; break validation into smaller tasks; provide additional support; adjust timeline if needed | Process Engineering Manager | 2025-11-07 | Open | Resource