## Risks
ID | Project | Title | Description | Likelihood | Impact | Mitigations | Owner | Date Identified | Status | Category
R001 | SF Documentation Optimization | NADCAP Audit Preparation Delay Risk | SF team being busy with many other tasks from wider stakeholders may cause delays in completing the NADCAP action plan and SF documentation review, potentially resulting in not being ready for the NADCAP Audit and pre-audit planned for March 26, 2025. | High | High | Prioritize NADCAP tasks; Assign dedicated resources; Weekly progress reviews; Escalate to management if delays occur | SF Team Lead | 2025-11-07 | Open | Schedule
R002 | SF Documentation Optimization | SF QMS Documentation Hierarchy Understanding Gap | If the documentation hierarchy is not fully understood, the overarching SF QMS document could contain inaccuracies, defeating the objective of providing clear signposting for anyone unfamiliar with SF documentation. | Medium | High | Conduct documentation hierarchy training; Create visual documentation map; Peer review of QMS structure; SME validation before finalization | QMS Lead | 2025-11-07 | Open | Quality
R003 | Surface Finish Table 1 Implementation Complete | Process Engineer Availability Risk | The process engineer responsible for validating Surface Finish Table 1 is heavily occupied with other tasks and may not complete the review within the given timeframe. | High | Medium | Identify backup engineer; Break validation into smaller milestones; Request management support for workload balancing; Set interim review checkpoints | Engineering Manager | 2025-11-07 | Open | Resource